## Sheet1
Assigned To | Updated To | Completed By | Priority | Related User Story | Task Description | Initial Estimate | Amount Remaining After…
[7 empty] | Week 1 | Week 2 | Week 3 | Week 4
Yeni |  | Yeni | 1.1 | Add Food Item To A Day | Hookup Add Buttons to Search Page | 3 | 3 | 0
Justin |  | Justin | 1.1 | Add Food Item To A Day | Search Process Client Side | 2.5 | 2 | 0
Yeni |  | Yeni | 1.2 | Add Food Item To A Day | Update FoodLog Process Client Side | 2.5 | 3 | 0
Justin |  | Justin | 1.2 | Add Food Item To A Day | Update FoodLog Process Server Side | 2.5 | 0 | 1.5
Yeni |  | Yeni | 1.3 | Add Food Item To A Day | Add Food Codebehind | 3 | 0 | 2
Emi |  | Emi | 1.4 | Add Food Item To A Day | Change Date of Food Log Client Side | 2
Victor | Justin | Justin | 1.4 | Add Food Item To A Day | Change Date of Food Log Server Side | 2 | 0 | 1.5
Justin |  | Justin | 2.1 | Display Daily Stats | Update HomeDashboard UI | 3 | 1.5 | 0
Emi |  | Emi | 2.1 | Display Daily Stats | Create Calculations Model | 2
Yeni |  | Emi | 2.2 | Display Daily Stats | Update HomeDashboard Codebehind | 3
Victor | Yeni | Yeni | 3.1 | Edit Diet | Account Menu UI | 5 | 0 | 3
Justin |  | Justin | 3.1 | Edit Diet | Edit Diet Process Client Side | 2.5 | 0 | 1.5
Emi | Justin | Justin | 3.1 | Edit Diet | Edit Diet Process Server Side | 2.5 | 0 | 1.5
Victor | Yeni | Yeni | 3.1 | Edit Diet | Edit Diet UI Page | 2 | 0 | 2
Emi | Yeni | Yeni | 3.2 | Edit Diet | Edit Diet Codebehind | 3 | 0 | 2
[5 empty] | Estimate Totals | 40.5 | 9.5 | 24.5 | 24.5 | 24.5
[6 empty] | 96 | 40.5 | 40.5 | 40.5 | 40.5
[5 empty] | Person | Current Hours | Total Hours For Sprint | Difference
[5 empty] | Justin | 10.5 | 10 | -0.5
[5 empty] | Emi | 9.5 | 10 | 0.5
[5 empty] | Yeni | 11.5 | 10 | -1.5
[5 empty] | Victor | 9 | 10 | 1