## Sheet1
Assigned To | Completed By | Priority | Related User Story | Task Description | Initial Estimate | Amount Remaining After…
[6 empty] | Week 1 | Week 2 | Week 3 | Week 4
Team |  | 1.1 | Login | Communication Protecol for authorization process | 0.75
Team |  | 1.1 | Login | User Class structure | 0.25
Emi |  | 1.2 | Login | Authorization Process Client Side | 4 | 4
Justin |  | 1.2 | Login | Authorization Process Server Side | 4
Victor |  | 1.2 | Login | Display logged in user's info on landing page | 2.5
Yeni |  | 1.2 | Login | Login UI Page | 2.75
Yeni |  | 1.3 | Login | Login Page Codebehind | 4
Team |  | 2.1 | Create Account | Communication Protecol for Create Account | 0.5
Team |  | 2.1 | Create Account | Credentials Structure | 0.25
Emi |  | 2.2 | Create Account | Create Account UI Page | 2.75
Justin |  | 2.2 | Create Account | Create Account Process Client Side | 4
Yeni |  | 2.2 | Create Account | Create Account Process Server Side | 4
Victor |  | 2.2 | Create Account | Display User Info on Landing After Creation | 2.5
Emi |  | 2.3 | Create Account | Create Account Page Code Behind | 4
Yeni |  | 3.2 | Create Food | Create Food Process Client Side | 4
Victor |  | 3.2 | Create Food | Create Food Process Server Side | 4
Team |  | 3.1 | Create Food | Communication Protecol for Create Food | 0.5
Team |  | 4.1 | Add Food Item To A Day | Communication Protecol for Search | 0.5
Team |  | 4.1 | Add Food Item To A Day | Communication Protecol for Update DayOfFood | 0.5
Team |  | 4.1 | Add Food Item To A Day | DayOfFood Structure | 0.5
Emi |  | 4.2 | Add Food Item To A Day | Fix UI Spacing Issues | 0.5
Emi |  | 4.2 | Add Food Item To A Day | Hookup Add Buttons to Search Page | 3
Yeni |  | 4.2 | Add Food Item To A Day | Hookup Remove Buttons to User | 3
Victor |  | 4.2 | Add Food Item To A Day | Search Process Client Side | 4
Justin |  | 4.2 | Add Food Item To A Day | Search Process Server Side | 4
Justin |  | 4.3 | Add Food Item To A Day | Update DayOfFood Process Client Side | 4
Victor |  | 4.3 | Add Food Item To A Day | Update DayOfFood Process Server Side | 4
Emi |  | 5.2 | Edit Diet | Edit Diet UI Page | 2
Emi |  | 5.2 | Edit Diet | Account Menu UI | 5
Justin |  | 5.3 | Edit Diet | Edit Diet Codebehind | 3
Victor |  | 5.2 | Edit Diet | Edit Diet Process Client Side | 4
Yeni |  | 5.2 | Edit Diet | Edit Diet Process Server Side | 4
Team |  | 5.1 | Edit Diet | Communication Protecol for Update Diet | 0.5
|  |  |  | Estimate Totals | 87.25 | 4 | 0 | 0 | 0
[5 empty] | 96 | 87.25 | 87.25 | 87.25 | 87.25
|  |  |  | Person | Current Hours | Total Hours For Sprint | Difference
|  |  |  | Justin | 19 | 24 | 0.75
|  |  |  | Emi | 21.25 | 24 | -1.5
|  |  |  | Yeni | 21.75 | 24 | -2
|  |  |  | Victor | 21 | 24 | -1.25
|  |  |  | Team | 4.25